# Pool Installation Analysis

Prepared by Cymbal Pools Operations for the regional installation teams. This document describes how Cymbal Pools scopes, inspects and schedules a residential in-ground pool installation.

# 1. How we conduct a pool site inspection

Confirm property lines, easements and setback requirements with the local permitting office before visiting the site.

Call 811 to locate buried utilities; mark gas, electric, water and irrigation lines within 3 m of the proposed excavation.

Assess access: the excavator needs a 3 m wide path; note gates, fences, trees and slopes that must be removed or protected.

Take soil samples at two depths. Expansive clay or a high water table requires an engineering review and may add a hydrostatic relief valve and gravel base.

Measure the slope across the pool footprint. More than 0.5 m of fall needs a retaining wall or raised beam design.

Identify the equipment pad location within 15 m of the pool and within reach of a dedicated electrical circuit.

Photograph the site from all four corners and record findings in the installation request before quoting.

# 2. Installation timeline

A standard 10 m x 5 m pool takes six to eight weeks: permits (1-2 weeks), excavation (2 days), steel and plumbing (1 week), shotcrete and cure (2 weeks), tile and coping (1 week), plaster, fill and start-up (1 week).

# 3. Common add-ons

Hot tubs are requested on roughly a third of installations and add about two weeks. Waterfalls and rock features add one week. Splash pads are increasingly requested for families with young children.

# 4. Recording a new request

Every request is recorded in the installation_requests table with the pool dimensions in metres, add-on flags, zip code, customer contact details and the request date.